## schedule
Item | Author | Draft ETA | Reviewer | Reviewer ETA | Ready for Editor ETA | Status | Notes
OData Core - Overview | Arlo | Done | mflasko / pablo | ? |  | Not Started
OData Core – Data Model | MikeF | 2012-02-13 | pablo | ? |  | In Progress
OData Core - Glossary | All | ? | ? | ? |  | Not Started
OData Core – Notational Conventions | Arlo | ? | ? | ? |  | Not Started
OData Core - Versioning | MikeP | Done | mflasko | 2012-02-20 |  | In Progress
OData Core – Extensibility | MikeP | Done | alexj | 2012-02-20 |  | In Progress
OData Core – Interaction Semantics – Metadata – Svc Doc | MikeF | 2012-02-15 | MikeP | 2012-02-20 |  | Not Started
OData Core – Interaction Semantics – Metadata – MD Doc | Alex/MikeF | 2012-02-07 | alexj | 2012-02-13 |  | In Progress
OData Core – Interaction Semantics – Query | MikeF/MikeP | ? | Andy | ? |  | Not Started
OData Core – Interaction Semantics – Data Modification | Arlo | ? | MFlasko | ? |  | Not Started
OData Core – Interaction Semantics – Actions no examples | Alex | Done | MikeP | 2012-02-20 |  | In Progress
OData Core – Interaction Semantics – Actions examples | Alex | 2012-02-15 | MikeP | 2012-02-20 |  | In Progress
OData Core – Interaction Semantics – Functions | Alex | 2012-02-15 | MikeP | 2012-02-25 |  | In Progress
OData Core – Interaction Semantics – Service Ops | Alex | 2012-02-17 | MikeP | 2012-02-25 |  | Not Started
OData Core – Appendix – Formal CSDL description | MarkS (MikeP/F backups) | 2012-02-29 | alexj | 2012-03-03 |  | Not Started
OData Core – Appendix – XSD for CSDL | MarkS | 2012-02-29 | ? | ? |  | Not Started
URI glossary terms (service root, etc) | AlexJ | 2012-02-20 | Mflasko | 2012-02-23 |  | Not Started
URI - Addressing conventions (consider using odata.org as base) | AlexJ | 2012-02-24 | Mflasko | 2012-02-23 |  | Not Started
URI - Addressing - SOPS, Actions, Functions | AlexJ | 2012-02-29 | Arlo | ? |  | Not Started
Atom Format | MikeP | 2012-02-24 | Mflasko, Arlo | 2012-02-27 |  | Not Started
JSON Format (efficient format) + its vocab | Arlo | ? | Pablo, MikeP | ? |  | Not Started
JSON (classic version) | Arlo | ? | Pablo, MikeP | ? |  | Not Started
Batch | MikeF | 2012-02-15 | Pablo | ? |  | In Progress
Work Items
Create table of doc names and short ref tags | mflasko | 2012-02-14

## status
Status
Not Started
Writing
Reviewing
Editing
Complete