## schedule
Item | Author | Draft ETA | Reviewer | Reviewer ETA | Ready for Editor ETA | Status | Notes
OData Core - Overview | Arlo | Done | mflasko | 2012-03-18 |  | Not Started
OData Core – Data Model | MikeF | 2012-02-21 | pablo | ? |  | In Progress
OData Core - Glossary | All | ? | ? | ? |  | Not Started
OData Core – Notational Conventions | Arlo | Done | alexj | ongoing |  | In Progress
OData Core - Versioning | MikeP | Done | mflasko | 2012-02-22 |  | In Progress
OData Core – Extensibility | MikeP | Done | alexj | 2012-02-21 |  | In Progress
OData Core – Interaction Semantics – Metadata – Svc Doc | MikeF | 2012-02-22 | MikeP | 2012-02-23 |  | Not Started
OData Core – Interaction Semantics – Metadata – MD Doc | MikeF | 2012-02-21 | alexj | 2012-02-22 |  | In Progress
OData Core – Interaction Semantics – Query | MikeF/MikeP | ? | Andy | ? |  | Not Started
OData Core – Interaction Semantics – Data Modification | Arlo | 2012-03-02 | MFlasko | 2012-03-08 |  | In Progress
OData Core – Interaction Semantics – Actions no examples | Alex | Done | MikeP | 2012-02-21 |  | In Progress
OData Core – Interaction Semantics – Actions examples | Alex | 2012-02-20 | MikeP | 2012-02-25 |  | In Progress
OData Core – Interaction Semantics – Functions | Alex | 2012-02-20 | MikeP | 2012-02-25 |  | In Progress
OData Core – Interaction Semantics – Service Ops | Alex | 2012-02-20 | MikeP | 2012-02-25 |  | Not Started
OData Core – Appendix – 2 initial sections | MikeP | 2012-02-21 | alexj | 2012-02-22 |  | Not Started
OData Core – Appendix – Formal CSDL description | MarkS | 2012-02-29 | alexj | 2012-03-03 |  | Not Started
OData Core – Appendix – XSD for CSDL | MarkS | 2012-02-29 | ? | ? |  | Not Started
URI glossary terms (service root, etc) | AlexJ | 2012-02-24 | Mflasko | 2012-02-28 |  | Not Started
URI - Addressing conventions (consider using odata.org as base) | AlexJ | 2012-02-28 | Mflasko | 2012-02-29 |  | Not Started
URI - Addressing - SOPS, Actions, Functions | AlexJ | 2012-03-02 | Arlo | 2012-03-06 |  | Not Started
Atom Format | MikeP | 2012-02-24 | Mflasko, Arlo | 2012-02-27 |  | In Progress
JSON Format (efficient format) + its vocab | Arlo | ? | Pablo, MikeP | ? |  | Not Started
JSON (verbose version) | Arlo | 2012-03-09 | Pablo, MikeP | 2012-03-15 |  | Not Started
Batch | MikeF | Done | Pablo | ? |  | In Progress
Work Items
Create table of doc names and short ref tags | mflasko | Done

## status
Status
Not Started
Writing
Reviewing
Editing
Complete

## Document Names & Abbreviations
Document Names | Abbreviations | Relative URLs to the Docs
Open Data Protocol | [OData:Core] | <some base>/odata
OData: AtomPub Format | [OData:AtomPub] | <some base>/atom
OData: JSON Verbose Format | [OData:JSONVerbose] | <some base>/jsonverbose
OData: JSON | [OData:JSON] | <some base>/json
OData: Batch Processing | [OData:Batch] | <some base>/batch