## schedule
Item | Author | Draft ETA | Reviewer | Reviewer ETA | Ready for Editor ETA | Status | Notes
OData Core | [5 empty] | Not Started
OData Core - Overview | Arlo | Done |  |  |  | Not Started
OData Core – Data Model | MikeF | 2012-01-13 |  |  |  | Not Started
OData Core - Terminology | All |  |  |  |  | Not Started
OData Core – Notational Conventions | Arlo |  |  |  |  | Not Started
OData Core - Versioning | MikeP |  |  |  |  | Not Started
OData Core – Extensibility | MikeP |  |  |  |  | Not Started
OData Core – Interaction Semantics – Metadata – Svc Doc | MikeP |  |  |  |  | Not Started
OData Core – Interaction Semantics – Metadata – MD Doc | Alex |  |  |  |  | Not Started
OData Core – Interaction Semantics – Query | MikeF/MikeP |  |  |  |  | Not Started
OData Core – Interaction Semantics – Data Modification | [5 empty] | Not Started
OData Core – Interaction Semantics – Actions | Alex |  |  |  |  | Not Started
OData Core – Interaction Semantics – Functions | Alex |  |  |  |  | Not Started
OData Core – Interaction Semantics – Service Ops | [5 empty] | Not Started
OData Core – Interaction Semantics – Batch Costs | [5 empty] | Not Started
OData Core – Appendix – Formal CSDL description | [5 empty] | Not Started
OData Core – Appendix – XSD for CSDL | [5 empty] | Not Started
URI - XXX | Alex |  |  |  |  | Not Started
Atom - XXX | MikeP |  |  |  |  | Not Started
JSON - XXX | Arlo |  |  |  |  | Not Started
JSON (with metadata) - XXX | Arlo |  |  |  |  | Not Started
Batch - XXX | MikeF |  |  |  |  | Not Started

## status
Status
Not Started
Writing
Reviewing
Editing
Complete